## Sheet1
SELECT & PREPARE A CONSTRUCTION CONTRACT
PREPARATION OF SCHEDULE OF PROGRESS PAYMENT VALUATIONS
SCHEDULE OF PRICED QUANTITIES
PROJECT SUMMARY
|  |  | TRADE SECTION |  | COST
| 1 | PRELIMINARIES |  |  | 7675
| 2 | SITEWORKS |  |  | 4145
| 3 | CONCRETEWORK |  |  | 6177
| 4 | BRICKWORK |  |  | 16397.8
| 5 | METALWORK |  |  | 5716.15
| 6 | CARPENTRY |  |  | 7153.59
| 7 | JOINERY |  |  | 2689.7
| 8 | CABINETWORK |  |  | 2420
| 9 | ROOFING |  |  | 7920
| 10 | ROOF PLUMBING |  |  | 2004.4
| 11 | SOLID PLASTERING |  |  | 6520
| 12 | SHEET PLASTERING |  |  | 2970
| 13 | WALL & FLOOR TILING |  |  | 1776.6
| 14 | GLASSWORK |  |  | 320
| 15 | PAINTWORK |  |  | 4090.14
| 16 | PLUMBING & GAS SERVICES |  |  | 10780
| 17 | ELECTRICAL SERVICES |  |  | 7695
|  | NET COST ESTIMATE - Excluding G.S.T |  |  | 96450.38
PROGRESS PAYMENT
QUANTITIES - PRICING SCHEDULE | [7 empty] | Enter % complete
[8 empty] | 1 | 2 | 3 | 4 | 5
[8 empty] | Slab | Bwk | Roof | Lock | Final
SECTION: | SUB SECTION | Item | Description | unit | Qty | Rate | Cost | down | Comp | cover | up | amt
excl GST
SITEWORKS | Sub contract (materials & labour) | 1 | engineer certificate | Item | 1 | 150 | 150 | 100% | 100% | 100% | 100% | 100%
|  | 2 | termite treatment: Spraying | m2 | 90 | 5.5 | 495 | 100% | 100% | 100% | 100% | 100%
|  | 3 | OR: Termi-mesh | unit: m; Qty: 0; Rate: 15; Cost: 0; amt: 100%
|  | 4 | Penetrations | unit: no.; Qty: 0; Rate: 20; Cost: 0; amt: 100%
| Provisional sum | 5 | cut & fill | item | 1 | 3500 | 3500 | 100% | 100% | 100% | 100% | 100%
|  |  | SUB-TOTAL | Rate: SITEWORKS; Cost: 4145
CONCRETE | Materials | 1 | concrete in footings | m3 | 4.8 | 145 | 696 | 100% | 100% | 100% | 100% | 100%
|  | 2 | concrete in ground slab | m3 | 10 | 145 | 1450 | 100% | 100% | 100% | 100% | 100%
|  | 3 | Trench mesh to footings | length | 8 | 28 | 224 | 100% | 100% | 100% | 100% | 100%
|  | 4 | Fabric mesh to ground slab | sheet | 7 | 65 | 455 | 100% | 100% | 100% | 100% | 100%
|  | 5 | polyethene sheeting - 4m wide | m | 26 | 2 | 52 | 100% | 100% | 100% | 100% | 100%
|  | 6 | Bar chairs | no. | 150 | 0.5 | 75 | 100% | 100% | 100% | 100% | 100%
|  | 7 | delivery: Rienforcement, Plastic, Bar chairs | item | 1 | 100 | 100 | 100% | 100% | 100% | 100% | 100%
| Labour | 8 | labour to set out ,excavate and place concrete in footings | m3 | 4.8 | 65 | 312 | 100% | 100% | 100% | 100% | 100%
|  | 9 | labour to form up, prepare and place concrete in ground slab | m3 | 10 | 65 | 650 | 100% | 100% | 100% | 100% | 100%
| Sub contract (materials & labour) | 10 | Curing of concrete slab | m2 | 84 | 4.5 | 378 | 100% | 100% | 100% | 100% | 100%
|  | 11 | setout, form, pour and finish concrete to carport, verndah, driveway and crossover | m2 | 51 | 35 | 1785 | 100% | 100% | 100% | 100% | 100%
|  |  | SUB-TOTAL | Rate: CONCRETEWORK; Cost: 6177
BRICK WORK | Materials | 1 | Face bricks 230x110x76mm | thou | 4.092 | 750 | 3069 |  | 100% | 100% | 100% | 100%
| Check PC amounts | 2 | Common bricks 305x90x162mm | thou | 2.583 | 500 | 1291.5 |  | 100% | 100% | 100% | 100%
| stated in Spec | 3 | Longreach bricks 305x90x76mm | thou | 0.252 | 950 | 239.4 |  | 100% | 100% | 100% | 100%
|  | 4 | Solid Sill- face brick | thou | 0.0495 | 850 | 42.075 |  | 100% | 100% | 100% | 100%
|  | 5 | deliver brick - face & commons | thou | 6.9765 | 50 | 348.825 |  | 100% | 100% | 100% | 100%
|  | 6 | sand | m3 | 5 | 15 | 75 |  | 100% | 100% | 100% | 100%
|  | 7 | cement 40kg | bag | 21 | 9 | 189 |  | 100% | 100% | 100% | 100%
|  | 8 | lime 20kg | bag | 14 | 6 | 84 |  | 100% | 100% | 100% | 100%
|  | 9 | damp proof course additive | 4 litre | 4 | 10 | 40 |  | 100% | 100% | 100% | 100%
|  | 10 | wire ties in bundles of 100 | bundle | 300 | 7 | 2100 |  | 100% | 100% | 100% | 100%
|  | 11 | straps - tie down | no | 36 | 5 | 180 |  | 100% | 100% | 100% | 100%
|  | 12 | flashings | 6m roll | 5.6 | 20 | 112 |  | 100% | 100% | 100% | 100%
|  | 13 | delivery - sundry items | item | 1 | 100 | 100 |  | 100% | 100% | 100% | 100%
| Labour | 14 | Lay facings | thou | 4.105 | 1000 | 4105 |  | 100% | 100% | 100% | 100%
|  | 15 | Lay commons | thou | 2.822 | 1000 | 2822 |  | 100% | 100% | 100% | 100%
| Sub contract (materials & labour) | 16 | materials and labour to clean face brickwork | thou | 4 | 50 | 200 |  | 100% | 100% | 100% | 100%
| Scaffold | 17 | scaffold kit hire | item | 1 | 1000 | 1000 |  | 100% | 100% | 100% | 100%
|  | 18 | delivery of kit | item | 1 | 200 | 200 |  | 100% | 100% | 100% | 100%
|  | 19 | pick up kit | item | 1 | 200 | 200 |  | 100% | 100% | 100% | 100%
|  |  | SUB-TOTAL | Rate: BRICKWORK; Cost: 16397.8
METAL WORK | Materials | 1 | Aluminium window & sliding door frames - Lump sum quote | item | 1 | 5000 | 5000 |  | 50% | 50% | 100% | 100%
| - Door frames | 2 | 620 LH ( Standard or W.C ) | no | 1 | 50 | 50 |  | 100% | 100% | 100% | 100%
|  | 3 | 620 RH ( Standard or W.C ) | no |  | 50 | 0 |  | 100% | 100% | 100% | 100%
|  | 4 | 520 LH | no |  | 50 | 0 |  | 100% | 100% | 100% | 100%
|  | 5 | 520 RH | no |  | 50 | 0 |  | 100% | 100% | 100% | 100%
|  | 6 | 720 LH | no | 1 | 50 | 50 |  | 100% | 100% | 100% | 100%
|  | 7 | 720 RH | no | 0 | 50 | 0 |  | 100% | 100% | 100% | 100%
|  | 8 | 820 LH | no | 1 | 50 | 50 |  | 100% | 100% | 100% | 100%
|  | 9 | 820 RH | no | 2 | 50 | 100 |  | 100% | 100% | 100% | 100%
|  | 10 | Other _________________ | no |  |  | 0 |  | 100% | 100% | 100% | 100%
| - Lintels | 11 | 90 x 90 x 6 mm angle | m | 5.85 | 16 | 93.6 |  | 100% | 100% | 100% | 100%
|  | 12 | 90 x 90 x 8 mm angle | m | 6.45 | 19 | 122.55 |  | 100% | 100% | 100% | 100%
|  | 13 | 100 x 100 x 6 mm angle | m |  | 18 | 0 |  | 100% | 100% | 100% | 100%
|  | 14 | 100 x 100 x 8 mm angle | m |  | 20 | 0 |  | 100% | 100% | 100% | 100%
|  | 15 | 150 x 90 x 8 mm angle | m | 0 | 28 | 0 |  | 100% | 100% | 100% | 100%
|  | 16 | meterbox | no | 1 | 150 | 150 |  | 100% | 100% | 100% | 100%
|  | 17 | delivery | item | 1 | 100 | 100 |  | 100% | 100% | 100% | 100%
|  |  | SUB-TOTAL | Rate: METALWORK; Cost: 5716.15
CARPENT RY | Materials - ceiling framing | 1 | wall plates - 90 X 35 mm | m | 85.8 | 2.3 | 197.34 |  |  | 100% | 100% | 100%
|  | 2 | ceiling joists - 90 X 35 mm | m | 211.5 | 2.8 | 592.2 |  |  | 100% | 100% | 100%
|  | 3 | hanging beams - 170 X 35 mm | m | 36.3 | 5 | 181.5 |  |  | 100% | 100% | 100%
|  | 4 | hanging beams - 190 X 45 mm | m |  | 5.5 | 0 |  |  | 100% | 100% | 100%
|  | 5 | hanging straps | no | 76 | 0.15 | 11.4 |  |  | 100% | 100% | 100%
| - roof framing | 6 | rafters- 120 X 35 mm | m | 253.2 | 4 | 1012.8 |  |  | 100% | 100% | 100%
|  | 7 | rafters- ____ X ____ mm | unit: m; Cost: 0; cover: 100%; up: 100%; amt: 100%
|  | 8 | hips & Valleys - 170 X 35 mm | m | 37.5 | 5 | 187.5 |  |  | 100% | 100% | 100%
|  | 9 | valleys - 170 X 35 mm | m |  | 5 | 0 |  |  | 100% | 100% | 100%
|  | 10 | Valley boards 150 x 25mm | m | 7.2 | 4 | 28.8 |  |  | 100% | 100% | 100%
|  | 11 | ridge - 200 X 25 mm | m | 3.9 | 4.5 | 17.55 |  |  | 100% | 100% | 100%
|  | 12 | underpurlins - 100 X 75 mm | m | 18 | 8 | 144 |  |  | 100% | 100% | 100%
|  | 13 | collar tie - 120 X 35 mm | m | 13.5 | 4 | 54 |  |  | 100% | 100% | 100%
|  | 14 | struts - 75 X 75 mm | m | 27.6 | 7.5 | 207 |  |  | 100% | 100% | 100%
|  | 15 | Eaves trimmer &struts 70 x 35mm | m | 46.5 | 2.5 | 116.25 |  |  | 100% | 100% | 100%
|  | 16 | Eaves struts 40 x 19mm | m | 0 | 2 | 0 |  |  | 100% | 100% | 100%
|  | 17 | beams: ______ x ______ mm | m | 16.8 | 45 | 756 |  |  | 100% | 100% | 100%
|  | 18 | posts - _____ X _____ mm | m |  | 25 | 0 |  |  | 100% | 100% | 100%
|  | 19 | steel beams - 150UB14 | m | 6.6 | 55 | 363 |  |  | 100% | 100% | 100%
|  | 20 | Other _________________ | Cost: 0; cover: 100%; up: 100%; amt: 100%
| Linings - Eaves |  | Square metre rate | m2 |  | 7.5 | 0 |  |  | 100% | 100% | 100%
| - Verandah, carport | 21 | 2400 X 750 mm | No | 11 | 9 | 99 |  |  | 100% | 100% | 100%
| & gables | 22 | 1800 X 900 mm | No |  | 12.15 | 0 |  |  | 100% | 100% | 100%
|  | 23 | 2400 X 900 mm | No |  | 16.2 | 0 |  |  | 100% | 100% | 100%
|  | 24 | 2400 X 1200 mm | No |  | 21.6 | 0 |  |  | 100% | 100% | 100%
|  | 25 | 2700 X 900 mm | No | 2 | 18.225 | 36.45 |  |  | 100% | 100% | 100%
|  | 26 | 2700 X 1200 mm | No |  | 24.3 | 0 |  |  | 100% | 100% | 100%
|  | 27 | 3000 X 900 mm | No |  | 20.25 | 0 |  |  | 100% | 100% | 100%
|  | 28 | 3000 X 1200 mm | No | 4 | 27 | 108 |  |  | 100% | 100% | 100%
|  | 29 | jointing strip - 3m | lengths | 9 | 2.2 | 19.8 |  |  | 100% | 100% | 100%
| - mouldings | 30 | barge | m |  | 6 | 0 |  |  | 100% | 100% | 100%
|  | 31 | fascia -Metal | m | 48 | 8 | 384 |  |  | 100% | 100% | 100%
|  | 32 | Fascia Corners- External | no | 5 | 5 | 25 |  |  | 100% | 100% | 100%
|  | 33 | Fascia Corners- Internal | no | 1 | 5 | 5 |  |  | 100% | 100% | 100%
|  | 34 | Fascia - Joining sleeves | no | 3 | 7 | 21 |  |  | 100% | 100% | 100%
|  | 35 | Other _________________ | Cost: 0; cover: 100%; up: 100%; amt: 100%
| - sundries | 36 | bolts | no | 6 | 1 | 6 |  |  | 100% | 100% | 100%
|  | 37 | brackets | no |  | 2 | 0 |  |  | 100% | 100% | 100%
|  | 38 | delivery | item | 1 | 100 | 100 |  |  | 100% | 100% | 100%
| Labour | 39 | labour to erect roof framing | m2 | 124 | 20 | 2480 |  |  | 100% | 100% | 100%
|  | 40 | ditto. but lining | m2 | 0 | 7.5 | 0 |  |  | 100% | 100% | 100%
|  |  | SUB-TOTAL | Rate: CARPENTRY; Cost: 7153.59
JOINERY | Materials - doors / windows | 1 | Timber frame - size / type single standard frame | no | 1 | 200 | 200 |  | 100% | 100% | 100% | 100%
|  | 2 | external door - Size / type. Allow PC $300.00 | no | 1 | 300 | 300 |  |  | 100% | 100% | 100%
| - Internal doors | 3 | 520 mm | no |  | 40 | 0 |  |  | 100% | 100% | 100%
|  | 4 | 620 mm | no | 2 | 41 | 82 |  |  | 100% | 100% | 100%
|  | 5 | 720 mm | no | 1 | 40 | 40 |  |  | 100% | 100% | 100%
|  | 6 | 820 mm | no | 1 | 40 | 40 |  |  | 100% | 100% | 100%
| - mouldings | 7 | skirting 67 X 25 mm MDF | m | 75.6 | 2.5 | 189 |  |  | 100% | 100% | 100%
|  | 8 | Nosing 140 X 25 mm MDF | m | 7.2 | 15 | 108 |  |  | 100% | 100% | 100%
|  | 9 | Capping ____ X 25 mm MDF | m | 0 | 20 | 0 |  |  | 100% | 100% | 100%
|  | 10 | Scotia 28 X 28 mm MDF | m | 7.2 | 2.5 | 18 |  |  | 100% | 100% | 100%
|  | 11 | Trim 18 X 18 mm MDF | m | 5.7 | 2 | 11.4 |  |  | 100% | 100% | 100%
|  | 12 | Balustrade & handrail | m |  | 200 | 0 |  |  | 100% | 100% | 100%
| - shelving | 13 | Framing 42 X 19 mm mdf | m | 6.6 | 3 | 19.8 |  |  | 100% | 100% | 100%
|  | 14 | lining 450 mm wide melamine | m | 2.7 | 8.5 | 22.95 |  |  | 100% | 100% | 100%
|  | 15 | Hanging rail | m | 2.5 | 5 | 12.5 |  |  | 100% | 100% | 100%
|  | 16 | End / centre pillar | no | 4 | 5 | 20 |  |  | 100% | 100% | 100%
| - hardware | 17 | hinges | no | 3 | 10 | 30 |  |  | 100% | 100% | 100%
|  | 18 | External door furniture (PC $200.00) | no | 1 | 200 | 200 |  |  | 100% | 100% | 100%
|  | 19 | Passage sets | no | 0 | 45 | 0 |  |  | 100% | 100% | 100%
|  | 20 | Privacy sets | no | 6 | 50 | 300 |  |  | 100% | 100% | 100%
|  | 21 | Dummy sets | no |  | 36 | 0 |  |  | 100% | 100% | 100%
|  | 22 | Door buffers | no | 6 | 5 | 30 |  |  | 100% | 100% | 100%
|  | 23 | Weather seal | no | 1 | 20 | 20 |  |  | 100% | 100% | 100%
|  | 24 | toilet roll holder | no | 1 | 22 | 22 |  |  | 100% | 100% | 100%
|  | 25 | Towel rail | no | 1 | 35 | 35 |  |  | 100% | 100% | 100%
|  | 26 | delivery | item |  | 100 | 0 |  |  | 100% | 100% | 100%
| Labour - including fixing accessories | 27 | external door | no | 1 | 85 | 85 |  |  | 100% | 100% | 100%
|  | 28 | internal door | no | 6 | 40 | 240 |  |  | 100% | 100% | 100%
|  | 29 | skirtings | m | 65 | 3.5 | 227.5 |  |  | 100% | 100% | 100%
|  | 30 | nosing & scotia | m | 7.2 | 5 | 36 |  |  | 100% | 100% | 100%
|  | 31 | capping & scotia | m | 0 | 7.5 | 0 |  |  | 100% | 100% | 100%
|  | 32 | trim | m | 5.7 | 2 | 11.4 |  |  | 100% | 100% | 100%
|  | 33 | Door hardware/ latchsets | no | 7 | 40 | 280 |  |  | 100% | 100% | 100%
|  | 34 | Door buffers | no | 6 | 5 | 30 |  |  | 100% | 100% | 100%
|  | 35 | Weather seal | no | 1 | 10 | 10 |  |  | 100% | 100% | 100%
|  | 36 | Shelving - 450mm wide | m | 2.7 | 12 | 32.4 |  |  | 100% | 100% | 100%
|  | 37 | shelf framing 40 x 19 MDF | m | 2.7 | 2.5 | 6.75 |  |  | 100% | 100% | 100%
|  | 38 | toilet paper holder | no | 1 | 10 | 10 |  |  | 100% | 100% | 100%
|  | 39 | towel rail | no | 1 | 20 | 20 |  |  | 100% | 100% | 100%
|  |  | SUB-TOTAL | Rate: JOINERY; Cost: 2689.7
CABINET WORKS | Sub contract (materials & labour) | 1 | kitchen benches | unit: m; Qty: 3.2; Rate: 600; Cost: 1920; amt: 100%
|  | 2 | laundry benches | unit: m; Rate: 500; Cost: 0; amt: 100%
|  | 3 | vanity bench | unit: NO.; Qty: 1; Rate: 500; Cost: 500; amt: 100%
|  |  | SUB-TOTAL | Rate: CABINETWORK; Cost: 2420
ROOFING | Subcontract | 1 | roof tiles including battens | cover: 100%; up: 100%; amt: 100%
| (materials & labour) | 132 | m2 enter area here | item | 1 | 7920 | 7920 |  |  | 100% | 100% | 100%
|  |  | SUB-TOTAL | Rate: ROOFING; Cost: 7920
ROOF PLUMBING | Sub contract (materials & labour) | 1 | gutters: Type / size ___________ | m | 49 | 7 | 343 |  |  | 100% | 100% | 100%
|  | 2 | valley gutters | m | 3.8 | 5 | 19 |  |  | 100% | 100% | 100%
|  | 3 | Gutter straps | no | 50 | 1 | 50 |  |  | 100% | 100% | 100%
|  | 4 | downpipes: Type/ size ________ | m | 25.2 | 7 | 176.4 |  |  | 100% | 100% | 100%
|  | 5 | Soakwells | no | 7 | 200 | 1400 |  |  | 100% | 100% | 100%
|  | 6 | DP straps | no | 16 | 1 | 16 |  |  | 100% | 100% | 100%
|  |  | SUB-TOTAL | Rate: ROOF PLUMBING; Cost: 2004.4
SOLID PLASTER | Sub contract (materials & labour) | 1 | float & set to walls | m2 | 246 | 25 | 6150 |  |  |  | 100% | 100%
|  | 2 | Corner beads | no. | 18 | 15 | 270 |  |  |  | 100% | 100%
|  | 3 | Sand | m3 | 4 | 25 | 100 |  |  |  | 100% | 100%
|  |  | SUB-TOTAL | Rate: SOLID PLASTERING; Cost: 6520
SHEET PLASTER | Sub contract (materials & labour) | 1 | Plasterboard ceilings including standard cornice | m2 | 78 | 30 | 2340 |  |  |  | 100% | 100%
|  | 2 | Extra for Non-Standard cornices | m | 105 | 6 | 630 |  |  |  | 100% | 100%
|  |  | SUB-TOTAL | Rate: SHEET PLASTERING; Cost: 2970
TILING | Materials | 1 | wall tiles: PC $ 40 / m2 | unit: m2; Qty: 7.45; Rate: 40; Cost: 298; amt: 100%
|  | 2 | floor tiles: $ 40 /m2 | unit: m2; Qty: 9.94; Rate: 40; Cost: 397.6; amt: 100%
|  | 3 | Soap holder | unit: no; Qty: 2; Rate: 20; Cost: 40; amt: 100%
|  | 4 | division strips | unit: m; Qty: 2; Rate: 10; Cost: 20; amt: 100%
|  | 5 | delivery | unit: item; Qty: 1; Rate: 50; Cost: 50; amt: 100%
| Labour / preparation work | 6 | labour to lay wall tiles including supply of adhesive, grout etc. | unit: m2; Qty: 7.45; Rate: 40; Cost: 298; amt: 100%
|  | 7 | labour to lay floor tiles including supply of adhesive, grout etc. | unit: m2; Qty: 9.94; Rate: 40; Cost: 397.6; amt: 100%
|  | 8 | floor screed | unit: m2; Qty: 9.94; Rate: 10; Cost: 99.4; amt: 100%
|  | 9 | waterproofing | unit: m2; Qty: 5.2; Rate: 5; Cost: 26; amt: 100%
|  | 10 | brick build up - bath | unit: no; Qty: 1; Rate: 100; Cost: 100; amt: 100%
|  | 11 | brick build up -shower hob | unit: no; Qty: 1; Rate: 50; Cost: 50; amt: 100%
|  |  | SUB-TOTAL | Rate: WALL & FLOOR TILING; Cost: 1776.6
GLASS WORK | Sub contract (materials & labour) | 1 | glazing to timber frames | unit: m2; Qty: 0; Rate: 150; Cost: 0; amt: 100%
|  | 2 | mirrors | unit: m2; Qty: 1; Rate: 150; Cost: 150; amt: 100%
|  | 3 | Curtain rod | unit: no.; Qty: 1; Rate: 20; Cost: 20; amt: 100%
|  | 4 | shower screen - fixed panel | unit: no; Qty: 1; Rate: 150; Cost: 150; amt: 100%
|  | 5 | shower screen - sliding panel | unit: no; Rate: 400; Cost: 0; amt: 100%
|  | 6 | shower screen - pivotting door | unit: no; Rate: 500; Cost: 0; amt: 100%
|  |  | SUB-TOTAL | Rate: GLASSWORK; Cost: 320
PAINT WORK | Sub contract (materials & labour) | 1 | External metalwork : - gutters / fascia | unit: m; Qty: 48; Rate: 6; Cost: 288; amt: 100%
|  | 2 | flashings / valley gutter | unit: m; Qty: 3.74; Rate: 6; Cost: 22.44; amt: 100%
|  | 3 | downpipes | unit: m; Qty: 25.2; Rate: 6; Cost: 151.2; amt: 100%
|  | 4 | External timber - door & frame | unit: no; Qty: 1; Rate: 85; Cost: 85; amt: 100%
|  | 5 | rafters / beams | unit: m; Rate: 5; Cost: 0; amt: 100%
|  | 6 | post | unit: m; Rate: 5; Cost: 0; amt: 100%
|  | 7 | External other - wall linings | unit: m2; Rate: 15; Cost: 0; amt: 100%
|  | 8 | ceilings / eaves linings | unit: m2; Qty: 37; Rate: 10; Cost: 370; amt: 100%
|  | 9 | Interior - Walls - Solid plaster | unit: m2; Qty: 246; Rate: 7; Cost: 1722; amt: 100%
|  | 10 | ceilings - sheet plaster | unit: m2; Qty: 78; Rate: 8; Cost: 624; amt: 100%
|  | 11 | metalwork - door frames | unit: m; Qty: 6; Rate: 5; Cost: 30; amt: 100%
|  | 12 | timber - doors | unit: no; Qty: 6; Rate: 35; Cost: 210; amt: 100%
|  | 13 | - skirtings | unit: m; Qty: 65; Rate: 7.5; Cost: 487.5; amt: 100%
|  | 14 | - nosing & scotia | unit: m; Qty: 8; Rate: 10; Cost: 80; amt: 100%
|  | 15 | - capping & scotia | unit: m; Qty: 0; Rate: 10; Cost: 0; amt: 100%
|  | 16 | - other trim | unit: m; Qty: 4; Rate: 5; Cost: 20; amt: 100%
|  |  | SUB-TOTAL | Rate: PAINTWORK; Cost: 4090.14
PLUMBING & GAS SERVICES | Sub contract (materials & labour) | 1 | soil, waste, vent pipes and hot & cold water supply incl. connections to mains, fixtures & appliances and | item | 1 | 5000 | 5000 | 15% |  | 50% | 50% | 100%
|  | 2 | Gas services pipework | unit: item; Rate: 150; Cost: 0; amt: 100%
|  | 3 | gas points - internal | unit: no; Rate: 100; Cost: 0; amt: 100%
| Materials (Sanitary fixtures) | 4 | wc & cistern | unit: no; Qty: 1; Rate: 300; Cost: 300; amt: 100%
|  | 5 | vanity basin | unit: no; Qty: 1; Rate: 150; Cost: 150; amt: 100%
|  | 6 | wall basin | unit: no; Rate: 180; Cost: 0; amt: 100%
|  | 7 | bath | unit: no; Qty: 1; Rate: 250; Cost: 250; amt: 100%
|  | 8 | kitchen sink | unit: no; Qty: 1; Rate: 600; Cost: 600; amt: 100%
|  | 9 | laundry trough | unit: no; Qty: 1; Rate: 380; Cost: 380; amt: 100%
|  | 10 | Tapsets | unit: no; Qty: 5; Rate: 70; Cost: 350; amt: 100%
|  | 11 | delivery | unit: item; Qty: 1; Rate: 100; Cost: 100; amt: 100%
|  |  | standpipes | unit: no; Qty: 2; Rate: 100; Cost: 200; amt: 100%
| Materials - Appliances | 12 | Oven (PC - $1000.00) | unit: no; Qty: 1; Rate: 1000; Cost: 1000; amt: 100%
| Check amounts | 13 | Hot plates (PC $850.00) | unit: no; Qty: 1; Rate: 850; Cost: 850; amt: 100%
| stated in Spec | 14 | hot water unit (PC $1,500.00) | unit: no; Qty: 1; Rate: 1500; Cost: 1500; amt: 100%
|  | 15 | delivery | unit: no; Qty: 1; Rate: 100; Cost: 100; amt: 100%
|  |  | SUB-TOTAL | Rate: PLUMBING & GAS; Cost: 10780
ELECTRICAL SERVICES | Sub contract (materials & labour) | 1 | mains supply and connection to appliances & service points including: | item | 1 | 6000 | 6000 | 10% |  | 40% | 40% | 100%
|  | 2 | switchboard | unit: no; Qty: 1; Rate: 750; Cost: 750; amt: 100%
|  | 3 | underground power | unit: m or item; Qty: 1; Rate: 30; Cost: 30; amt: 100%
|  | 4 | single power point | unit: no; Qty: 9; Rate: 35; Cost: 315; amt: 100%
|  | 5 | double power point | unit: no; Qty: 0; Rate: 40; Cost: 0; amt: 100%
|  | 6 | ext. power point | unit: no; Qty: 0; Rate: 75; Cost: 0; amt: 100%
|  | 7 | light point | unit: no; Qty: 12; Rate: 35; Cost: 420; amt: 100%
|  | 8 | Light point - 2 - way | unit: no; Qty: 2; Rate: 50; Cost: 100; amt: 100%
|  | 9 | Exhaust fan | unit: no; Qty: 1; Rate: 80; Cost: 80; amt: 100%
|  | 10 | Extra for points in suspended slab | unit: no; Rate: 50; Cost: 0; amt: 100%
| Materials - Appliances | 11 | wall oven (PC $ 1000.00) | unit: no; Rate: 1000; Cost: 0; amt: 100%
| Check amounts | 12 | hot plate (PC $ 850.00) | unit: no; Rate: 850; Cost: 0; amt: 100%
| stated in Spec | 13 | delivery | unit: item; Rate: 50; Cost: 0; amt: 100%
|  |  | SUB-TOTAL | Rate: ELECTRICAL SERVICES; Cost: 7695
PRELIMIN ARIES |  | 1 | Building lic. Fee | CV | 0.35% | 100000 | 350 | 100% | 100% | 100% | 100% | 100%
|  |  | Water corp fees | item | 1 | 250 | 250 | 100% | 100% | 100% | 100% | 100%
|  | 2 | Training levy | CV | 0.2% | 100000 | 200 | 100% | 100% | 100% | 100% | 100%
|  | 2 | Site shed | week | 25 | 25 | 625 | 10% | 10% | 50% | 70% | 100%
|  | 3 | toilet | week | 25 | 40 | 1000 | 10% | 20% | 50% | 70% | 100%
|  | 4 | Progressive Site clean | no | 1 | 150 | 150 | 10% | 25% | 50% | 70% | 100%
|  | 5 | Final clean | no | 1 | 1000 | 1000 | 0% | 0% | 0% | 0% | 100%
|  | 6 | Insurances | item | 1 | 1500 | 1500 | 100% | 100% | 100% | 100% | 100%
|  | 7 | Handover | item | 1 | 500 | 500 | 0% | 0% | 0% | 0% | 100%
|  | 8 | footpath deposit | no | 2 | 50 | 100 | 100% | 100% | 100% | 100% | 100%
|  | 9 | Plant & equipment | item | 1 | 1000 | 1000 | 20% | 40% | 60% | 80% | 100%
|  | 10 | Defects liability | CV | 1% | 100000 | 1000 | 0% | 0% | 0% | 0% | 100%
|  |  | SUB-TOTAL |  |  | ELECTRICAL SERVICES | 7675 | 14449.5 | 33235.95 | 58491.14 | 71036.14 | 96450.38
[7 empty] | OVERALL % COMPLETE | 14.98% | 34.46% | 60.64% | 73.65% | 100%